## Jira
Issue id | Issue key | Summary | Issue Type | Status | Assignee | Created | Updated | Last Viewed | Resolved | Parent | Parent summary | Status Category | Status Category Changed
10000 | CPN-1 | Recommendations System | Epic | In Progress |  | 2024-04-03 20:26 | 2024-05-28 17:29 | 2024-05-30 23:02 |  |  |  | In Progress | 2024-05-28 17:06
10005 | CPN-6 | As a user, I want to search for groups freely just by name, so I will find exactly what Iג€™m looking for. | Task | To Do |  | 2024-04-03 20:28 | 2024-04-03 20:28 | 2024-05-30 23:02 |  | 10000 | Recommendations System | To Do | 2024-04-03 20:28
10006 | CPN-7 | As a community leader, I want my community to show up for people with specific interests, to advertise it but also to avoid having too many members. | Task | To Do |  | 2024-04-03 20:28 | 2024-04-03 20:28 | 2024-05-30 23:02 |  | 10000 | Recommendations System | To Do | 2024-04-03 20:28
10007 | CPN-8 | As a community leader, I want to be able to invite people to my community, to be able to advertise for specific people. | Task | To Do |  | 2024-04-03 20:28 | 2024-04-03 20:28 | 2024-05-30 23:02 |  | 10000 | Recommendations System | To Do | 2024-04-03 20:28
10008 | CPN-9 | As a user, I want proper communities to be advertised to me by default, so the usage of the app will be simpler and I won't have to always change my preferences. | Task | To Do |  | 2024-04-03 20:28 | 2024-04-03 20:28 | 2024-05-30 23:02 |  | 10000 | Recommendations System | To Do | 2024-04-03 20:28
10003 | CPN-4 | As a user, I want to get product recommendations, so I can get personalized options for new products to buy. | Task | In Progress | Eldor Zang | 2024-04-03 20:27 | 2024-05-28 16:45 | 2024-05-30 23:02 |  | 10000 | Recommendations System | In Progress | 2024-05-28 16:45
10031 | CPN-32 | Find a suitable dataset | Subtask | Done | Eldor Zang | 2024-05-28 16:46 | 2024-05-30 22:32 | 2024-05-30 23:02 | 2024-05-28 16:48 | 10003 | As a user, I want to get product recommendations, so I can get personalized options for new products to buy. | Done | 2024-05-28 16:48
10032 | CPN-33 | Design end to end ML pipeline | Subtask | Done | Eldor Zang | 2024-05-28 16:46 | 2024-05-30 22:32 | 2024-05-28 17:16 | 2024-05-28 16:46 | 10003 | As a user, I want to get product recommendations, so I can get personalized options for new products to buy. | Done | 2024-05-28 16:46
10033 | CPN-34 | Train with whole dataset | Subtask | In Progress | Eldor Zang | 2024-05-28 16:49 | 2024-05-28 17:07 | 2024-05-30 23:02 |  | 10003 | As a user, I want to get product recommendations, so I can get personalized options for new products to buy. | In Progress | 2024-05-28 17:07
10034 | CPN-35 | integrate the final model with the server and the android app | Subtask | To Do |  | 2024-05-28 16:49 | 2024-05-28 16:49 | 2024-05-30 23:02 |  | 10003 | As a user, I want to get product recommendations, so I can get personalized options for new products to buy. | To Do | 2024-05-28 16:49
10013 | CPN-14 | As a user, I want to be able to mark unwanted communities and block/report abusive or inactive communities, to be able to improve my recommendations and help the other users of the app. | Task | To Do |  | 2024-04-03 20:29 | 2024-04-03 20:29 | 2024-05-30 23:02 |  | 10000 | Recommendations System | To Do | 2024-04-03 20:29
10001 | CPN-2 | Coupon Management | Epic | In Progress |  | 2024-04-03 20:27 | 2024-05-28 17:12 | 2024-05-30 23:02 |  |  |  | In Progress | 2024-05-28 17:12
10014 | CPN-15 | As a user, I want my coupons to be automatically sorted by usable coupons and unusable ones by date or if Iג€™ve used them before, so they will be easier to manage. | Task | In Progress |  | 2024-04-03 20:29 | 2024-05-28 17:12 | 2024-05-30 23:02 |  | 10001 | Coupon Management | In Progress | 2024-05-28 17:12
10015 | CPN-16 | As a user, I want to be able to list coupons for sale in communities without revealing them, so that trading will be simpler. | Task | To Do |  | 2024-04-03 20:29 | 2024-04-03 20:29 | 2024-05-30 23:02 |  | 10001 | Coupon Management | To Do | 2024-04-03 20:29
10016 | CPN-17 | As a user, I want to be alerted about to-be-expired coupons, so that I will be able to sell them or use them before they lose their value. | Task | To Do |  | 2024-04-03 20:29 | 2024-04-03 20:29 | 2024-04-03 20:30 |  | 10001 | Coupon Management | To Do | 2024-04-03 20:29
10017 | CPN-18 | As a community leader, I want to be able to pin a specific trade, so that more people will see better trades. | Task | To Do |  | 2024-04-03 20:29 | 2024-04-03 20:29 | 2024-05-30 23:02 |  | 10001 | Coupon Management | To Do | 2024-04-03 20:29
10018 | CPN-19 | As a user, I want the coupons that can be used repeatedly to be added to a global list, so that everyone will be able to use them. | Task | To Do |  | 2024-04-03 20:29 | 2024-04-03 20:29 | 2024-05-30 23:02 |  | 10001 | Coupon Management | To Do | 2024-04-03 20:29
10002 | CPN-3 | UI | Epic | In Progress |  | 2024-04-03 20:27 | 2024-05-28 17:25 | 2024-05-28 17:25 |  |  |  | In Progress | 2024-05-28 17:12
10004 | CPN-5 | As a user, I want to be able to change my settings, so my account will be personalized. | Task | In Progress | Dor Sror | 2024-04-03 20:27 | 2024-05-28 17:13 | 2024-04-03 20:29 |  | 10002 | UI | In Progress | 2024-05-21 21:37
10019 | CPN-20 | Implement Settings activity in the app and save them locally. | Subtask | In Progress |  | 2024-05-21 21:15 | 2024-05-21 21:19 | 2024-05-30 23:02 |  | 10004 | As a user, I want to be able to change my settings, so my account will be personalized. | In Progress | 2024-05-21 21:19
10021 | CPN-22 | Implement login and register | Subtask | Done | Dor Sror | 2024-05-21 21:18 | 2024-05-28 17:06 | 2024-05-30 23:02 | 2024-05-21 21:19 | 10004 | As a user, I want to be able to change my settings, so my account will be personalized. | Done | 2024-05-21 21:19
10028 | CPN-29 | Implement main menu activity with all primary options of the app. | Subtask | Done | Dor Sror | 2024-05-21 21:34 | 2024-05-28 17:06 | 2024-05-30 23:02 | 2024-05-21 21:34 | 10004 | As a user, I want to be able to change my settings, so my account will be personalized. | Done | 2024-05-21 21:34
10035 | CPN-36 | Implement API end points for retrieving and updating user data | Subtask | Done | Eldor Zang | 2024-05-28 17:01 | 2024-05-30 22:32 | 2024-05-30 23:02 | 2024-05-28 17:01 | 10004 | As a user, I want to be able to change my settings, so my account will be personalized. | Done | 2024-05-28 17:01
10036 | CPN-37 | Implement database with user being the key and each filed is an attribute of the user | Subtask | Done | Eldor Zang | 2024-05-28 17:06 | 2024-05-30 22:32 | 2024-05-30 23:02 | 2024-05-28 17:06 | 10004 | As a user, I want to be able to change my settings, so my account will be personalized. | Done | 2024-05-28 17:06
10009 | CPN-10 | As a user, I want to see my coupons history, so in case that I forget I will be able to look for similar coupons. | Task | In Progress | Dor Sror | 2024-04-03 20:28 | 2024-05-28 17:13 | 2024-05-30 23:02 |  | 10002 | UI | In Progress | 2024-05-28 17:13
10023 | CPN-24 | Implement app activity to display used and inactive coupons (do not display sold coupons with their code) | Subtask | In Progress | Dor Sror | 2024-05-21 21:22 | 2024-05-28 17:14 | 2024-05-30 23:02 |  | 10009 | As a user, I want to see my coupons history, so in case that I forget I will be able to look for similar coupons. | In Progress | 2024-05-28 17:14
10024 | CPN-25 | Implement database with user being the key and list of coupons as the value | Subtask | Done | Eldor Zang | 2024-05-21 21:23 | 2024-05-30 22:32 | 2024-05-30 23:02 | 2024-05-28 17:03 | 10009 | As a user, I want to see my coupons history, so in case that I forget I will be able to look for similar coupons. | Done | 2024-05-28 17:03
10029 | CPN-30 | Add coupon display | Subtask | Done | Dor Sror | 2024-05-21 21:36 | 2024-05-29 16:21 | 2024-05-30 23:02 | 2024-05-29 16:21 | 10009 | As a user, I want to see my coupons history, so in case that I forget I will be able to look for similar coupons. | Done | 2024-05-29 16:21
10037 | CPN-38 | Implement API end points for retrieving and updating user's coupons | Subtask | Done | Eldor Zang | 2024-05-28 17:07 | 2024-05-30 22:32 | 2024-05-30 23:02 | 2024-05-28 17:07 | 10009 | As a user, I want to see my coupons history, so in case that I forget I will be able to look for similar coupons. | Done | 2024-05-28 17:07
10010 | CPN-11 | As a community leader, I want to be able to see all users sorted by activity and join date, so I will be able to manage inactive users and reward active ones. | Task | To Do |  | 2024-04-03 20:28 | 2024-04-03 20:28 | 2024-05-30 23:02 |  | 10002 | UI | To Do | 2024-04-03 20:28
10025 | CPN-26 | Implement community page - Title, Short description, Picture, Invite etc. | Subtask | In Progress |  | 2024-05-21 21:23 | 2024-05-21 21:33 | 2024-05-30 23:02 |  | 10010 | As a community leader, I want to be able to see all users sorted by activity and join date, so I will be able to manage inactive users and reward active ones. | In Progress | 2024-05-21 21:31
10026 | CPN-27 | Implement join date and activity in the community per user, visible only to the community's leaders. | Subtask | To Do |  | 2024-05-21 21:31 | 2024-05-21 21:31 | 2024-05-30 23:02 |  | 10010 | As a community leader, I want to be able to see all users sorted by activity and join date, so I will be able to manage inactive users and reward active ones. | To Do | 2024-05-21 21:31
10011 | CPN-12 | As a community leader, I want to be able to modify my communityג€™s appearance, so that it will fit the theme of the community better. | Task | To Do |  | 2024-04-03 20:28 | 2024-04-03 20:28 | 2024-05-30 23:02 |  | 10002 | UI | To Do | 2024-04-03 20:28
10027 | CPN-28 | After implementation of community page, add community settings and edit. | Subtask | To Do |  | 2024-05-21 21:32 | 2024-05-21 21:32 | 2024-05-30 23:02 |  | 10011 | As a community leader, I want to be able to modify my communityג€™s appearance, so that it will fit the theme of the community better. | To Do | 2024-05-21 21:32
10030 | CPN-31 | Add option to add/delete community leaders/moderators | Subtask | To Do |  | 2024-05-21 21:36 | 2024-05-21 21:36 | 2024-05-30 23:02 |  | 10011 | As a community leader, I want to be able to modify my communityג€™s appearance, so that it will fit the theme of the community better. | To Do | 2024-05-21 21:36
10012 | CPN-13 | As a user, I want to see if people who invite me as a friend are a good match with me, so I will be able to differentiate between relevant users and irrelevant users. | Task | To Do |  | 2024-04-03 20:28 | 2024-04-03 20:28 | 2024-05-30 23:02 |  | 10002 | UI | To Do | 2024-04-03 20:28
10020 | CPN-21 | Implement Friends list | Subtask | To Do |  | 2024-05-21 21:16 | 2024-05-21 21:16 | 2024-05-30 23:02 |  | 10012 | As a user, I want to see if people who invite me as a friend are a good match with me, so I will be able to differentiate between relevant users and irrelevant users. | To Do | 2024-05-21 21:16
10022 | CPN-23 | Implement user-user recommendation system and check match percentage | Subtask | To Do |  | 2024-05-21 21:18 | 2024-05-21 21:18 | 2024-05-30 23:02 |  | 10012 | As a user, I want to see if people who invite me as a friend are a good match with me, so I will be able to differentiate between relevant users and irrelevant users. | To Do | 2024-05-21 21:18